## Slide 1: STOCK MARKET DATA
Project purpose: Create an interactive dashboard using html, JavaScript, css and using external public APIs (through RapidAPI) to fetch data of top 7 tech companies and display their performance over the 23 years since Jan 1st, 2000 till end of 2023.
Display the growth of $1000 over these 2 years if invested in these stocks and compare the performance of multiple stocks in a single line graph.
Stocks include the following
Company name | Stock Ticker
Apple | AAPL
Tesla | TSLA
Microsoft | MSFT
Netflix | NFLX
Meta | META
Google | GOOG
NVDIA | NVDA

## Slide 2: STOCK MARKET INTERACTIVE DASHBOARD
Drop Down Menu for user
Select the stock you want to see the performance for
Drop down with inputs to select multiple stocks at the same time
Select the stocks you want to compare performance for
YEARS
STOCK PRICE
YEARS
$1000 Investment results

## Slide 3: WORK BREAKDOWN STRUCTURE (WBS)
Sl No | Task Title | Sub tasks | Task Owner | Start Date | End Date | Status
1 | Project kick-off | Ideation Project identification Project finalization through discussion with team members | Ipsita Siobhan Drew | 4/4/2024 | 4/4/2024 | Completed
2 | Github Repo creation | Create 3 branches | Ipsita | 4/5/2024 | 4/6/2024 | Completed
3 | Prototype preparation | Prepare a prototype of the project | Ipsita | 4/5/2024 | 4/6/2024 | Completed
4 | Data collection / extraction | Pull JSON data through URL - https://rapidapi.com/letscrape-6bRBa3QguO5/api/real-time-finance-data | Ipsita | 4/5/2024 | 4/6/2024 | Completed
5 | Data preparation | Data extraction from public API load into MongoDB (No SQL DB) | Ipsita | 4/6/2024 | 4/7/2024 | Completed
6 | Development and coding | Individual modules to be divided among team members | Ipsita Siobhan Drew | 4/8/2024 | 4/12/2024 | In progress
7 | Validation and testing | Testing individual modules Integration testing Smoke testing Regression testing | Ipsita Siobhan Drew | 4/15/2024 | 4/17/2024 | Planned
8 | Project completion and final presentation | Presentation of individual modules | Ipsita Siobhan Drew | 4/18/2024 | 4/18/2024 | Planned